## Tasks
Task | Urgency | Importance | efforts in weeks | Category | comment | start_date | end_date | Duration in days | disruption factor
nisl condimentum id | 0.86 | 0.08 | 1 | Scale better |  | 2022-04-08 | 2022-04-15 | 7 | 1
venenatis a condimentum | 0.52 | 0.35 | 2 | Iterate faster |  | 2022-04-11 | 2022-04-25 | 14
vitae sapien pellentesque habitant | 0.98 | 0.6 | 1 | Cost optimization |  | 2022-04-20 | 2022-04-27 | 7
morbi tristique senectus et netus et malesuada | 0.72 | 0.54 | 3 | Cost optimization |  | 2022-04-21 | 2022-05-12 | 21
fames ac turpis egestas sed tempus urna et pharetra | 0.33 | 0.48 | 2 | SDLC / Ops |  | 2022-04-26 | 2022-05-10 | 14
pharetra massa massa ultricies mi quis hendrerit | 0.59 | 0.47 | 3 | IT/infosec |  | 2022-05-04 | 2022-05-25 | 21
dolor magna eget est lorem ipsum dolor sit amet | 0.95 | 0.59 | 8 | Iterate faster |  | 2022-05-05 | 2022-06-30 | 56
consectetur adipiscing elit pellentesque habitant | 0.51 | 0.59 | 6 | SDLC / Ops |  | 2022-05-09 | 2022-06-20 | 42
morbi tristique senectus et netus et malesuada | 0.51 | 0.15 | 6 | Scale better |  | 2022-05-12 | 2022-06-23 | 42
fames ac turpis egestas integer eget aliquet | 0.49 | 0.15 | 10 | Tech Debt |  | 2022-05-25 | 2022-08-03 | 70
nibh praesent tristique magna sit amet purus | 0.81 | 0.33 | 7 | Tech Debt |  | 2022-05-27 | 2022-07-15 | 49
gravida quis blandit turpis cursus in hac | 0.72 | 0.36 | 2 | Tech Debt |  | 2022-06-02 | 2022-06-16 | 14
habitasse platea dictumst quisque sagittis | 1 | 0.02 | 3 | Tech Debt |  | 2022-06-03 | 2022-06-24 | 21
purus sit amet volutpat consequat mauris nunc | 0.03 | 0.66 | 4 | Cost optimization |  | 2022-06-08 | 2022-07-06 | 28
congue nisi vitae suscipit tellus mauris a diam | 0.57 | 0.8 | 2 | Tech Debt |  | 2022-06-13 | 2022-06-27 | 14
maecenas sed enim ut sem viverra aliquet eget sit | 0.24 | 0.5 | 4 | IT/infosec |  | 2022-06-15 | 2022-07-13 | 28
amet tellus cras adipiscing enim eu turpis egestas | 0.17 | 0.23 | 12 | Scale better |  | 2022-06-16 | 2022-09-08 | 84
pretium aenean pharetra magna ac placerat vestibulum | 0.24 | 0.51 | 20 | Iterate faster |  | 2022-06-17 | 2022-11-04 | 140
lectus mauris ultrices eros in cursus turpis massa | 0.47 | 0.02 | 12 | Iterate faster |  | 2022-06-20 | 2022-09-12 | 84
tincidunt dui ut ornare lectus sit amet est placerat | 0.89 | 0.83 | 4 | Scale better |  | 2022-06-21 | 2022-07-19 | 28
in egestas erat imperdiet sed euismod nisi porta | 0.26 | 0.69 | 2 | Tech Debt |  | 2022-06-23 | 2022-07-07 | 14
lorem mollis aliquam ut porttitor leo a diam | 0.58 | 0.39 | 30 | Cost optimization |  | 2022-06-27 | 2023-01-23 | 210
sollicitudin tempor id eu nisl nunc mi ipsum | 0.8 | 0.4 | 8 | IT/infosec |  | 2022-07-07 | 2022-09-01 | 56
faucibus vitae aliquet nec ullamcorper sit amet | 0.61 | 0.04 | 5 | Scale better |  | 2022-07-12 | 2022-08-16 | 35
risus nullam eget felis eget nunc lobortis mattis | 0.98 | 0.18 | 10 | SDLC / Ops |  | 2022-07-21 | 2022-09-29 | 70
aliquam faucibus purus in massa tempor nec feugiat | 0.6 | 0.86 | 3 | SDLC / Ops |  | 2022-07-22 | 2022-08-12 | 21
nisl pretium fusce id velit ut tortor pretium | 0.74 | 0.74 | 8 | Scale better |  | 2022-07-22 | 2022-09-16 | 56
Formulas:
end_date = IF(NOT(ISBLANK(Table2[[#This Row],[start_date]])),Table2[[#This Row],[start_date]] + Table2[[#This Row],[efforts in weeks]]*7*J2,"")
Note on J1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Used to calculate how much time it will take in absolute

## Matrix
Urgent
Important
Not Urgent
Not important

## Tasks by category
Tasks | Sum of efforts in weeks
Cost optimization | 38
lorem mollis aliquam ut porttitor leo a diam | 30
morbi tristique senectus et netus et malesuada | 3
purus sit amet volutpat consequat mauris nunc | 4
vitae sapien pellentesque habitant | 1
IT/infosec | 15
maecenas sed enim ut sem viverra aliquet eget sit | 4
pharetra massa massa ultricies mi quis hendrerit | 3
sollicitudin tempor id eu nisl nunc mi ipsum | 8
Iterate faster | 42
dolor magna eget est lorem ipsum dolor sit amet | 8
lectus mauris ultrices eros in cursus turpis massa | 12
pretium aenean pharetra magna ac placerat vestibulum | 20
venenatis a condimentum | 2
Scale better | 36
amet tellus cras adipiscing enim eu turpis egestas | 12
faucibus vitae aliquet nec ullamcorper sit amet | 5
morbi tristique senectus et netus et malesuada | 6
nisl condimentum id | 1
nisl pretium fusce id velit ut tortor pretium | 8
tincidunt dui ut ornare lectus sit amet est placerat | 4
SDLC / Ops | 21
aliquam faucibus purus in massa tempor nec feugiat | 3
consectetur adipiscing elit pellentesque habitant | 6
fames ac turpis egestas sed tempus urna et pharetra | 2
risus nullam eget felis eget nunc lobortis mattis | 10
Tech Debt | 26
congue nisi vitae suscipit tellus mauris a diam | 2
fames ac turpis egestas integer eget aliquet | 10
gravida quis blandit turpis cursus in hac | 2
habitasse platea dictumst quisque sagittis | 3
in egestas erat imperdiet sed euismod nisi porta | 2
nibh praesent tristique magna sit amet purus | 7
(blank)
(blank)
Grand Total | 178